## Requirements
Number | Statement | Met?
Section 1 | Authentication
1.1 | Users and administrators shall log into the system with unique usernames associated with passwords
1.2.1 | Admins shall be able to add sites
1.2.2 | Admins shall be able to edit sites
1.2.3 | Admins shall be able to remove sites
Section 2 | User Functions
2.1 | The user shall be able to identify start and end "waypoints"
Section 3 | System Functions
3.1 | The system shall provide help files for users and admins
3.2 | The system shall calculate the shortest route between all locations, starting at the chosen start waypoint and terminating at the chosen end waypoint
3.3 | The system shall display the calculated route on Google Earth
3.4 | The system shall provide a list of at least 20 sites to choose from
3.5 | The system shall associate each site with its correct latitude and longitude
3.6 | The system shall include all US national parks as waypoints
3.7 | The system shall include Machu Picchu as a waypoint
3.8 | The system shall calculate the final route distance
3.9 | The system shall include a facts display for each waypoint
Section 4 | Platform
4.1 | User actions shall be performed in a graphical user interface
4.2 | The GUI shall be blue and green

## Deliverables
Number | Name | Status | Deadline | Notes
Section 1 | The Product | Developing
1.1 | Executable
1.2 | Source Code |  |  | Extensively commented
1.3 | Administrator Manual |  |  | Hardcopy required
Section 2 | The Documentation | Developing |  | To be compiled in a 3-ring binder, along with item 1.3
2.1 | README
2.2 | System Requirements Specification |  |  | Hardcopy required
2.3 | System Design Document |  |  | Hardcopy required
2.4 | UI Design Document |  |  | Hardcopy required
2.5 | Code Inspection Work
2.6 | Test Report

## Issues
Number | Name | Status | Notes
1 | Git project needs setting up for project development | Unresolved | This is an example