## Requirements
Number | Statement | Met?
Section 1 | Authentication
1.1 | Users and administrators shall log into the system with unique usernames associated with passwords
Section 2 | User Functions
2.1 | The user shall be able to identify start and end "waypoints"
2.2 | Admins shall be able to add sites
2.3 | Admins shall be able to edit sites
2.4 | Admins shall be able to remove sites
Section 3 | System Functions
3.1 | The system shall provide help files for users and admins
3.2 | The system shall calculate the shortest route between all locations, starting at the chosen start waypoint and terminating at the chosen end waypoint
3.3 | The system shall display the calculated route on Google Earth
3.4 | The system shall provide a list of at least 20 sites to choose from
3.5 | The system shall associate each site with its correct latitude and longitude
3.6 | The system shall include all US national parks as waypoints
3.7 | The system shall include Machu Picchu as a waypoint
3.8 | The system shall calculate the final route distance
3.9 | The system shall include a facts display for each waypoint
Section 4 | Platform
4.1 | User actions shall be performed in a graphical user interface
4.2 | The GUI shall be blue and green

## Functional Flow Table
Number | Name | Description | Requirement # | Requirement Name
Section 1 | Setup | Functions required for basic interaction
1.1 | LoadGUI | Display visually the window of operation to the user. | 1.1 | Show GUI
1.2 | Login | Modifies the GUI to allow interactions based on user permissions. Requires the input of a known username/password combination | 1.2 | Logs in
1.3 | Logoff | Reverts the GUI to initial state, removing all interactions except the option to input a username and password. | 1.3 | Logs off
Section 2 | User Interaction | Functions outside of Section 1 that require a user trigger.
2.1.1 | SelectStart | The user chooses a start waypoint, and the system flags this as the starting location in route calculations. | 3.1 | Prompt waypoints
2.1.2 | SelectEnd | The user chooses an end waypoint, and the system flags this as the final location in route calculations. | 3.2 | Prompt waypoints
2.2 | AddWaypoint (ADMIN) | The user inputs a name, lat/long coordinate pair and description for a new waypoint, which is then stored in the database. | 2.1 | Adds waypoint
2.3 | RemoveWaypoint (ADMIN) | The user selects a waypoint by name, and upon confirmation this waypoint is removed from the database. | 2.2 | Deletes waypoint
2.4 | EditWaypoint (ADMIN) | The user selects a waypoint by name, and a new panel appears in the GUI to edit the details of this waypoint. | 2.3 | Edit waypoint information
2.4.1 | ChangeName (ADMIN) | The user inputs a new name for the waypoint, which is then changed in the GUI and database. | 2.3 | Edit waypoint information
2.4.2 | ChangeCoordinates (ADMIN) | The user inputs a new lat/long coordinate pair for the waypoint, which is then changed in the GUI and database. | 2.3 | Edit waypoint information
2.4.3 | ChangeDescription (ADMIN) | The user inputs a new description for the waypoint, which is then changed in the GUI and database. | 2.3 | Edit location information
Section 3 | System Functions | Functions that act within the syste, without user interaction.
3.1 | DisplayHelp | Upon selection of this option, the user will be shown a help file with detailed information on all available functions for their permission level. | 3.2 | Get Help
3.2 | CalculateRoute | The system calculates the shortest straight-line path between every waypoint in the list, starting at the selected start and terminating at the selected end. | 4.1 | Calculate Route
3.3 | DisplayRoute | The system queries Google Earth to display the calculated route. | 4.3 | Display Route
3.4 | GenerateWaypointList | The system pulls all available waypoints from the database to provide a list to the user. | 3.1.1 | Show Waypoints
3.5 | CalculateDistance | The system calculates the total distance of the route based on lat/long changes. | 4.2 | Find Distance

## Deliverables
Number | Name | Status | Date of Completion | Deadline | Notes
Section 1 | The Product | Developing
1.1 | Executable
1.2 | Source Code |  |  |  | Extensively commented
1.3 | Administrator Manual |  |  |  | Hardcopy required
Section 2 | The Documentation | Developing |  |  | To be compiled in a 3-ring binder, along with item 1.3
2.1 | README
2.2 | System Requirements Specification |  |  |  | Hardcopy required
2.3 | System Design Document |  |  |  | Hardcopy required
2.4 | UI Design Document |  |  |  | Hardcopy required
2.5 | Code Inspection Work
2.6 | Test Report

## Issues
Number | Name | Status | Notes | Projected Resolution Date
1 | Git project needs setting up for project development | Unresolved | This is an example | 2013-10-17
2 | Customer MIA | Resolved | New customer acquired | 2013-10-12

## Databases
Waypoint Table Structure
Name | Lat (+- .0001) | Long (+- .0001) | Description
User Table
Name | Password | Admin? (boolean)

## Defect Checklist
Name | Category | Description