## Sheet1
ID | Sprint | Theme | Role | Task | Reason | LOE | Time spent | Time Left | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | Note
1.1 | 1 | Preparation | Team | Planning | To develop requirements | 1 | 6 | 0 | [18 empty] | Effective start date delayed until week 6 due to lack of a customer. | bar: 1 to 6
1.2 | 1 | Design & Documentation | Team | SRR, SRS | To agree on requirements | 2 | 3 | 0 | 7: 1; 8: 2
2.1 | 2 | Design & Documentation | Team | SDR, SDD | To develop design | 1 | 3 | 0 | 8: 1; 9: 2
3.1 | 3 | Design & Documentation | Team | SSR, UIDD | To agree on design | 2 | 2 | 0 | bar: 9
3.2 | 3 | Design & Documentation | Team | PDR | To agree on design | 1 | 1 | 0 | [18 empty] | Chris is having difficulties on UI | bar: 10
4.1 | 4 | Coding | Christopher | GUI Development | For ease of user interaction | 3 | 3 | 1 | 11: 2; 12: 1
4.2 | 4 | Coding | Mariama, Michael | Path Routing Algorithms | For functionality requirements | 3 | 3 | 1 | bar: 11 to 12
4.3 | 4 | Coding | Justin, Stephen | Google Earth Integration | To meet specified external requirements | 3 | 3 | 1 | 11: 1; 12: 2
4.4 | 4 | Coding | Keith | Database Development | To maintain required user data | 3 | 4 | 1 | 11: 1; 12: 3
5.1 | 5 | Testing | Team | Testing | To test functionality | 2 | 3 | 1 | 13: 3
5.2 | 5 | Testing | Team | CIR, TRR | To report on functionality | 3 | 3 | 2 | bar: 13
5.3 | 5 | Testing | Team | Testing 2 | To test readiness | 3 | 3 | 2 | [18 empty] | Thanksgiving | bar: 13
5.4 | 5 | Testing & Documentation | Team | TR, AM, UM | To report on delivery readiness | 2 | 2 | 3 | bar: 14
6.1 | 6 | Delivery | Team | Admin/User docs | To compile final deliverables | 4 | 4 | 3 | 14: 2; 15: 1 | High LOE due to time constraints
6.2 | 6 | Demonstrations | Team | Demo | To present final deliverables | 2 | 2 | 4 | [18 empty] | Demo is either W15 or W16 | bar: 15 to 16
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
[7 empty] | 0 | 0
|  |  |  | TOTAL |  | 35 | 45 | 19 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 5 | 7 | 5 | 3 | 2 | 1 | 0 | 0
|  |  |  | Daily burnout |  | -44 |  |  | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 5 | 4 | 4 | 5 | 4 | 4 | 4 | 5 | 4 | 4
|  |  |  | Total time left (from estimate) |  |  | Estimate | 35 | 30 | 26 | 21 | 17 | 12 | 8 | 3 | -1 | -6 | -10 | -14 | -19 | -23 | -27 | -31 | -36 | -40 | -44
|  |  |  | Total time left (from spent) |  |  | Burnout | 45 | 44 | 43 | 42 | 41 | 40 | 39 | 38 | 35 | 32 | 31 | 26 | 19 | 14 | 11 | 9 | 8 | 8 | 8